## RDS Action Plan 2017-2020
Rural Development Strategy of Georgia Action Plan 2017
Priority Measure |  | Activity | Indicators of Implementation | Responsible Authority | Partner Organization | Terms of Implementation | Preliminary Budget (GEL) | Source of Funding | Comments
1. Objectives in the Field of Economy and Competitiveness
1.1 | Competitiveness Improvement of the economic side of the farming business, restructuring and modernization through diversification and development of the supply chain. | 1.1.1 Facilitation of the opening of new enterprises and/or expansion of the existing ones within the agriculture sector through the preferential agro credit programme | Financial support will be provided to 110 new and existing enterprises for expansion /technological upgrade/ modernisation | Ministry of Agriculture of Georgia | N(N)LE Agricultural Projects Management Agency (APMA); Commercial Banks | 2017 | 47000000 | State Budget
|  | 1.1.2 Reduction of risks and improving the competitiveness of agro-production by providing agro-insurance | Insurance of plots of up to 5,000 Ha | Ministry of Agriculture of Georgia | N(N)LE Agricultural Projects Management Agency (APMA); | 2017 | 7000000 | State Budget
|  | 1.1.3 Facilitate the creation of new intensive/semi-intensive fruit gardens and high quality nursery gardens within the framework of state program 'Plant the Future' | 700 ha of new modern intensive and semi-intensive perennial garden plantation Plantation of two new nursery gardens | Ministry of Agriculture of Georgia | N(N)LE Agricultural Projects Management Agency (APMA); Commercial Banks | 2017 | 7000000 | State Budget
|  | 1.1.4 Facilitation of Georgian tea production within the state program 'Georgian Tea' | Area of rehabilitated tea plantations estimated to be 180 Ha | Ministry of Agriculture of Georgia | N(N)LE Agricultural Projects Management Agency (APMA); | 2017 | 400000 | State Budget
|  | 1.1.5 Facilitation of agro processing and storage enterprise creation | Financial support will be provided for creation of at least 6 enterprises | Ministry of Agriculture of Georgia | N(N)LE Agricultural Projects Management Agency (APMA); Commercial Banks | 2017 | 5000000 | State Budget
|  | 1.1.6 Modernization/improvement of the amelioration systems located in rural areas in order to increase fertility | Improvement of water supply system to 7,500 Ha of ameliorated land New arable lands are adapted - approximately 130 Ha Rehabilitated of dried land - approximately 1,600 Ha Around 800 km of irrigation and drainage channels will be cleaned and improved 70 km of pipeline will be repaired and replaced | Ministry of Agriculture of Georgia | JSC Georgian Amelioration | 2017 | 48000000 | State Budget
|  | 1.1.7 Facilitate the export of Georgian agro products through promotional means | Participate in at least 10 international exhibitions to increase Georgian wine and agro-product awareness | Ministry of Agriculture of Georgia | LEPL National Wine Agency | 2017 | 6000000 | State Budget
|  | 1.1.8 Facilitate the establishment of co-operatives via the support of agro co-operatives in order to promote entrepreneurialship in rural areas | Up to approximately 10 cooperatives are equipped with grape and/or milk receiving-manufacturing equipment Approximately 28 cooperatives are equipped with honey and bee products production equipment (hives, strainers, tanks, honeycomb cutter) International standards will be implemented (Iso, Global Gap, Haccp) in approximately 7 cooperatives | Ministry of Agriculture of Georgia | LEPL Agricultural Cooperatives Development Agency | 2017 | 4870000 | State Budget
1.2 | Diversification. Diversification of rural economy through strengthening of the agriculture related value chain and development of sustainable non-agricultural direction | 1.2.1. Support industrial, micro and small size entrepreneurs via the 'Produce in Georgia' state program | • Number of projects: up to 150 • Amount of total investment: GEL 320 million • Number of jobs created: up to 8,000 • Number of micro and small enterprises (beneficiaries) created in the region: up to 1,300 • Number of trained beneficiaries: up to 3,000 | LEPL Entrepreneurship Development Agency | Ministry of Economy and Sustainable Development of Georgia; LEPL National Agency of State Property; LEPL-Agricultural Project Management Agency | QI of 2017 – QIV of 2017 | 32050000 | State Budget | Project has been implemented since 2016 and will be continued in 2017
1.3 | Rural tourism. Development of tourism and tourism products in rural areas based on the rural area and its unique cultural identity | 1.3.1. Facilitate hotel development through the hotel hotel industry support component via the 'Produce in Georgia' state program | • Number of projects: up to 30 • Amount of total investment: up to GEL 40 million • Number of jobs created: up to 800 • Number of new rooms: up to 700 | LEPL Entrepreneurship Development Agency | Ministry of Economy and Sustainable Development of Georgia | QI of 2017 – QIV of 2017 | 1500000 | State Budget | Project has been implemented since 2016 and will be continued in 2017
|  | 1.3.2. Encourage internal/domestic tourism | At least 15 events accomplished throughout Georgia | LEPL Georgian National Tourism Administration | Ministry of Economy and Sustainable Development of Georgia | QI of 2017 – QIV of 2017 | 450000 | State Budget
|  | 1.3.3. Small tourism infrastructure development | 40 installed notice-boards 30 tourist routs designated with signs | LEPL Georgian National Tourism Administration | Ministry of Economy and Sustainable Development of Georgia | QI of 2017 – QIV of 2017 | 670000 | State Budget
|  | 1.3.4 Development of tourism products in order to increase tourism in rural areas | 5 new and renovated tourism products At least 20 hiking trails are elaborated | LEPL Georgian National Tourism Administration | Ministry of Economy and Sustainable Development of Georgia | QI of 2017 – QIV of 2017 | 165000 | State Budget
|  | 1.3.5. Small infrastructure development via the Wine Route project for the facilitation of wine tourism development in rural areas | At least 180 (road) signs are installed throughout Georgia | LEPL Georgian National Tourism Administration | Ministry of Economy and Sustainable Development of Georgia | QI of 2017 – QIV of 2017 | 300000 | State Budget
|  | 1.3.6. Private sector skill development in terms of tourism services (retraining program) | At least 700 representatives of the private sector are retrained | LEPL Georgian National Tourism Administration | Ministry of Economy and Sustainable Development of Georgia | QI of 2017 – QIV of 2017 | 240000 | State Budget
2. Objectives in the Field of Social Conditions and Living Standards
2.1 | Skills and employment Increase awareness regarding innovation and entrepreneurship. Encourage partnership (especially among youth and women) by facilitating skill-development and employment | 2.1.1. Provision of general and specialized training via Innovation Centers in order to facilitate innovation development in rural areas | Up to 1,500 trained beneficiaries | LEPL Georgia’s Innovation and Technology Agency | World Bank; Private sector; USAID ZRDA; USAID G4G | I qtr. of 2017 – IV qtr. of 2017 | 100000 | State Budget
|  | 2.1.2. Organizing promotional events for the popularization and development of innovation | Up to 10 conducted contests, Olympic contests, exhibitions, conferences | LEPL Georgia’s Innovation and Technology Agency | World Bank | QI of 2017 – QIV of 2017 | 50000 | State Budget
|  | 2.1.3. Increase the accessibility of vocational education in municipalities and constituent villages | Vocational education program beneficiaries (students) increased by 5% compared to baseline indicator of (7,580) | Ministry of Education and Science of Georgia |  | QI of 2017 – QIV of 2017 | 11115000 | State Budget
|  | 2.1.4. Orientation and preparatory courses for the students from the regions | Orientation and preparatory courses for students from regions are offered in at least five schools (baseline indicator 0) | Ministry of Education and Science of Georgia | UNDP | QI of 2017 – QIV of 2017 | 224300 | State Budget and Donor Organizations
|  | 2.1.5. Initiate/introduce modular educational programs (dual approach) in agriculture in order to improve the quality of vocational education | 3 programs implemented in the agriculture sector on the dual approach basis (baseline indicator is 0) | Ministry of Education and Science of Georgia | UNDP GIZ | QI of 2017 – QIV of 2017 | 1494900 | State Budget and Donor Organizations
|  | 2.1.6. Provide the IDPs wishing to settle in the rural areas with accommodation in places where the land plots are available together with housing | 400 IDP households receive housing with land plot | Ministry of Internally Displaced Persons from the Occupied Territories, Accommodation and Refugees of Georgia |  | QI of 2017 – QIV of 2017 | 8000000 | State Budget
|  | 2.1.7. Provision of Georgian language courses at public centers of villages with densely-populated ethnical groups in order to facilitate their employment in future | At least 30 inhabitants of rural areas successfully complete Georgian language courses | LEPL Public Service Development Agency | Training Center of the Ministry of Justice of Georgia; | QI of 2017 – QIV of 2017 | 7760 | State Budget; Donor Organizations
|  | 2.1.8. Increase the opportunities of employment/self-employment of rural population through vocational trainings-retraining and qualification growth of the job-seekers | At least 300 job-seekers are retrained in the regions of Georgia | Ministry of Labor, Health and Social Affairs of Georgia | LEPL Social Service Agency Ministry of Education and Science of Georgia | QI of 2017 – QIV of 2017 | 30000 | State Budget
|  | 2.1.9. Facilitation of the employment of the rural population through encouragement of professional development at the municipality level | At least 40 job-seekers from four regions of Georgia received consultations in their profession and services related to career planning | Ministry of Labor, Health and Social Affairs of Georgia | LEPL Social Service Agency | QI of 2017 – QIV of 2017 | 48000 | State Budget
|  | 2.1.10. Facilitate vulnerable, low competitive groups via the development of cooperation with the interested parties | To facilitate the employment of the vulnerable, the low competitiveness groups salary subsidy is developed At least 10 people with disabilities and students with special needs receive adequate service | Ministry of Labor, Health and Social Affairs of Georgia | LEPL Social Service Agency | QI of 2017 – QIV of 2017 | 3000 | State Budget
|  | 2.1.11. Organize job fairs to facilitate the employment in rural population | At least one job fair is organized At least 150 job-seekers from the regions of Georgia participate in job fair | Ministry of Labor, Health and Social Affairs of Georgia | LEPL Social Service Agency | QI of 2017 – QIV of 2017 | 15000 | State Budget
2.2 | Infrastructure and services Improvement of the basic rural infrastructure (including roads leading to cultural heritage destinations and related infrastructure) and expand the availability of high-quality public services including the information and communication technology | 2.2.1. Creation of Innovation Centres throughout Georgia for the development of innovation | 10 equipped and operational innovation centres in towns and villages | LEPL Georgia’s Innovation and Technology Agency | World Bank | QI of 2017 – QIV of 2017 | 1200000 | State Budget
|  | 2.2.2. Provide rural populations with high-quality primary healthcare services including: a) improving the medical services of the village doctor - Target: 2.0 visits per beneficiary in 2017. (2015 indicator is 1.7 visits per beneficiary) b) Improving the provision of emergency services in rural areas. | a) Increase in the number of visits per beneficiary from 1.7 to 2.0 b) Emergency services available in every rural community across the country 24 hours a day (from 87 locations) | Ministry of Labor, Health and Social Affairs of Georgia | a) LEPL Social Service Agency b) LEPL Medical Emergency Center (regional); | QI of 2017 – QIV of 2017 | a) 26 000 000.0 b) 22 266 000.0 | State Budget
|  | 2.2.3. Improvement of road infrastructure in rural areas | 250 km of local roads are paved or rehabilitated | Municipalities | Ministry of Regional Development and Infrastructure of Georgia | QI of 2017 – QIV of 2017 | 50000000 | Local Budget; State Budget; Donor Organizations
|  | 2.2.4. Facilitate pre-school education in rural areas | Up to 70 newly-constructed or rehabilitated kindergartens are established | Municipalities | Ministry of Regional Development and Infrastructure of Georgia | QI of 2017 – QIV of 2017 | 10000000 | Local Budget; State Budget; Donor Organizations
|  | 2.2.5. Facilitation of sports and culture in rural areas | Up to 25 constructed/rehabilitated sports and cultural facilities are established | Municipalities | Ministry of Regional Development and Infrastructure of Georgia | QI of 2017 – QIV of 2017 | 5000000 | Local Budget; State Budget; Donor Organizations | Partnership with the Ministry of Regional Development and Infrastructure organizes coordination of state entities with municipalities
|  | 2.2.6. Prevention and liquidation of the disastrous effects of flooding and deluge | Up to 20 km of draining systems installed/rehabilitated | Municipalities | Ministry of Regional Development and Infrastructure of Georgia | QI of 2017 – QIV of 2017 | 2000000 | Local Budget; State Budget; Donor Organizations | Partnership with the Ministry of Regional Development and Infrastructure organizes coordination of state entities with municipalities
|  | 2.2.7. Water supply system rehabilitation in rural areas | Up to 300km water supply system constructed/rehabilitated and up to 20 water treatment plants built/rehabilitated | Municipalities | Ministry of Regional Development and Infrastructure of Georgia | QI of 2017 – QIV of 2017 | 12000000 | Local Budget; State Budget; Donor Organizations | Partnership with the Ministry of Regional Development and Infrastructure organizes coordination of state entities with municipalities
|  | 2.2.8. Provide a gas supply to the regions, including the rural population | Gasification work conducted 35,000 new potential customers will be added | Ministry of Energy of Georgia | JSC Socar Georgia Gas; JSC Georgian Gas Transportation Company | QI of 2017 – QIV of 2017 | 35,310,000.0 20,000,000.0 | State Budget; Private investment
|  | 2.2.9. Increase accessibility of public services for the rural population by providing additional service centers | Additional public centres are built and 48 centres operate across Georgia (three are based in libraries) More than 200 public services are accessible via public centers At least an additional 15,000 citizens from rural areas have access to public cervices through public centers | LEPL Public Service Development Agency | Municipalities; LEPL "National Agency of Public Registry"; LEPL "National Archive of Georgia"; LEPL "Notary Chamber of Georgia"; LEPL "Social Service Agency"; LTD Mechanizatori", Legal Aid Service; Liberty Bank; LTD "Magticom" | QI of 2017 – QIV of 2017 | 1110600 | LEPL Public Service Development Agency's Budget; International organization (EU)
|  | 2.2.10. Improvement of municipal services for the rural population and the establishment of Municipality Management Systems (MMS) for this purpose | Additional public libraries (at least 1), using the public center concept In 50 municipalities overall, MMS system is operational with various services | LEPL Public Service Development Agency | Partners: LEPL"Data Exchange Agency", LEPL "National Agency of Public Registry"; LEPL "Smart Logic", LEPL " Training Center of Justice of Georgia", LEPL "Financial-Analytical Service" (Ministry of Finance); Society of International Cooperation of Germany (GIZ) | QI of 2017 – QIV of 2017 | 134900 | Donor Organization (EU)
|  | 2.2.11. Increase accessibility to modern public libraries and public services for the rural population - modernization of additional public libraries using the concept of public centers | Two additional modern public libraries operate using the public center concept At least 15 employees of public libraries are retrained in various towns and villages | LEPL Public Service Development Agency | Municipalities, Georgian Association of Libraries, National Library of Georgian Parliament | QI of 2017 – QIV of 2017 | GEL315,605.0 9,000.0 USD | Budget of the LEPL Public Service Development Agency; Donor Organizations (EU; IREX)
|  | 2.2.12. Insuring accessibility to notary services in municipal centers where such services were not accessible in 2016 inter alia not accessible for village populations in the vicinity/neighborhood of such centers) | 15 well equipped notary bureaus are established in rural areas | LEPL Notary Chamber of Georgia | Ministry of Justice of Georgia | QI of 2017 – QIV of 2017 | 100000 | Budget of LEPL Notary Chamber of Georgia | Notary Chamber will provide various financial and material assistance to notary officers
|  | 2.2.13 Increase taxpayers' accessibility to the Revenue Service (RS) in regions, where RS does not have representation, via mobile service center "RSCAR" (providing all needed services) | In 2017, on average, 6,500 taxpayer will receive service in 33 regions | LEPL - Revenue Service | Ministry of Finance of Georgia | I Q 2017 - IV Q 2017 | 73000 | State Budget
2.3 | Local population inclusion Increasing the inclusion of the rural population (especially youth and women) in determining the local needs and in finding the ways of solving these needs | 2.3.1. Facilitation of women’s activity and inclusion via the use of public centers | At least six events related to women's rights and gender equality are conducted | LEPL Public Service Development Agency | Ministry of Justice of Georgia; Women’s Information Center; LEPL Training Center of Justice of Georgia; Other Non-governmental Organizations | I Q 2017 - IV Q 2017 | 15000 | EU; SIDA; Partner Organizations
|  | 2.3.2. Increase the awareness of the rural population on legal migration and the rights of migrants (on the basis of public centers) | At least 10 informative meetings are conducted | LEPL Public Service Development Agency | Women’s Information Center; Training Center of Justice of Georgia; Other Non-governmental Organizations | I Q 2017 - IV Q 2017 | 25000 | EU; SIDA; Partner Organizations
3. Objectives in the Field of Environment and Sustainable Natural Resources Management
3.1 | Water, wood and other resources Improvement in the management of water, forest and other resources in targeted rural areas | 3.1.1 Elaboration and implementation of the optimal forest classification system for the sustainable usage of forest resources (including by the rural population ) | New Code of Forest determining the forest classification (including protected areas, recreation zones, protective and farm forests) rules is adopted | Ministry of Environment and Natural Resources Protection of Georgia | LEPL National Forestry Agency World Bank Society of International Cooperation of Germany (GIZ) | I Q 2017 - IV Q 2017 | 20000 | Donor Organizations
|  | 3.1.2. Provision of the sustainable use of biological resources of natural pastures | Sustainability of the Vashlovani, Lagodekhi and Tusheti Protected Areas is evaluated Sustainable management plan (pilot) of the Vashlovani, Lagodekhi and Tusheti Protected Areas is elaborated and approved | Ministry of Environment and Natural Resources Protection of Georgia | LEPL Agency of Protected Areas Municipalities International Donor Organizations | I Q 2017 - IV Q 2017 | 100000 | Donor Organizations | Will continue in 2018 as well
3.2 | Waste Management Support the development of sustainable waste management systems in rural areas | 3.2.1 Improvement of municipal waste management | First five-year plans of municipal waste management are elaborated | Municipalities | Ministry of Environment and Natural Resources Protection of Georgia Ministry of Regional Development and Infrastructure of Georgia International Organizations | I Q 2017 - IV Q 2017 | 50000 | International Donor Organizations | Will continue in 2018 as well
|  |  | Biodegradable waste utilization pilot project is implemented at least in one municipality | Ministry of Environment and Natural Resources Protection of Georgia | Municipalities Non-governmental Organizations International Organizations. | I Q 2017 - IV Q 2017 | 100000 | State Budget International Donor Organizations USAID | Will continue until 2019
|  | 3.2.2. Improvement of waste management in the protected areas | Guidelines for waste management in the protected areas is elaborated | Ministry of Environment and Natural Resources Protection of Georgia | LEPL Agency of Protected Areas Non-governmental Organizations International Organizations. | I Q 2017 - IV Q 2017 | 60000 | International Donor Organizations | Will continue until 2019
3.3 | Climate change Implementation of mitigation measures for the potential negative impacts caused by climate change. Risk assessment | 3.3.1. Improvement/development of agro-meteorology in order to prevent future natural calamities/disasters | Number of reconstructed and operating agro-meteorological stations | Ministry of Environment and Natural Resources Protection of Georgia | Ministry of Agriculture of Georgia LEPL National Environment Agency EU International Organizations | I Q 2017 - IV Q 2017 | 50000 | State Budget International Donors | Will continue in 2018 as well
|  | 3.3.2 Increase the awareness of local government on climate change in terms of the risks to bio-diversity and agriculture | A number of seminars were conducted for local governments | Ministry of Environment and Natural Resources Protection of Georgia | Municipalities International Donor Organizations Non-governmental Organizations | I Q 2017 - IV Q 2017 | 50000 | International Donors | Will continue in 2018 as well